EXERCISE 02

Weekly Team Meeting Notes

Raw notes - intentionally incomplete and partly contradictory

## Meeting details

Date: Monday, 10 August 2026 | Time: 09:00-10:05 | Chair: Operations Manager

Present: Administration - Rima; Accounting - Tarek; Marketing - Noor; Training Coordination - Maya; IT - Karim; Managing Director - joined at 09:40.

## Raw notes

Python Fundamentals has 11 confirmed students. Room B fits 10 comfortably. Maya suggested moving to Room A; Karim said Room A projector flickers.

Decision sounded like: use Room A if projector is fixed by Thursday. Nobody was clearly assigned to check the projector.

AutoCAD campaign: Noor will prepare visuals by Wednesday. Later she said the designer cannot deliver until Thursday afternoon.

Website schedule still shows the old Revit start date. Rima said she can update it, but Karim usually controls the page. No owner confirmed.

Corporate Excel proposal for Cedar Foods: send by Tuesday? Tarek wrote Wednesday in his notebook. Pricing still needs MD approval.

Two instructor invoices are missing tax details. Tarek will send them back today and close August payroll by Friday.

Students requested recorded sessions for Digital Marketing. Team agreed recordings may be shared only with enrolled students for 30 days.

Photography field visit: Saturday 22 August mentioned, but the course calendar says Saturday 29 August. Maya to verify - no deadline stated.

Open issue: decide whether to add a second Python cohort if inquiries reach 18. Current inquiry count reported as 16, but administration sheet showed 17.

Next meeting: Monday at 09:00. Someone should bring the room-capacity options and the Cedar Foods proposal status.