## Contract Data
Malaeb Engineering & Contracting SAL
Achrafieh Medical Centre - Contract Data
Client | Achrafieh Medical Holding SAL
Client contact | Rania Haddad, Development Director
Contract sum | USD 6,850,000
Contract completion date | 4 September 2026
Current forecast completion | 16 October 2026 (42 calendar days late)
Liquidated damages rate | USD 4,500 per calendar day beyond the contract completion date
Liquidated damages accrued at forecast | USD 189,000 (42 days x USD 4,500)
Retention | 5%, released 50% at practical completion and 50% at end of 12-month defects liability period
Applications certified to date | Application 5, certified 30 October 2025
Application 6 status | Submitted 2 December 2025, unpaid at 41 days as of this schedule
Generator variation | Submitted 14 November 2025, USD 68,400, not yet instructed by the client

## Programme
Achrafieh Medical Centre - Programme Extract
Key activities only. Total float shown; negative float = critical path driver.
ID | Activity | Planned Start | Planned Finish | Forecast Finish | Total Float (days) | % Complete | Notes
A10 | Substructure & Foundations | 2025-01-15 | 2025-04-30 | 2025-04-28 | 0 | 1 | Complete, 2 days ahead
A20 | Superstructure - Levels 1-4 | 2025-05-01 | 2025-09-15 | 2025-09-20 | -5 | 1 | Completed 5 days late, absorbed
A30 | Facade & Envelope | 2025-08-01 | 2025-12-15 | 2025-12-28 | -13 | 0.85 | Shop drawing delays, recovery plan in place
A40 | Chilled-Water Piping Package (imported) | 2025-10-01 | 2025-11-30 | 2026-01-20 | -42 | 0.3 | Held at Beirut port since 18 November - the critical driver
A41 | Level 2 Electrical Rough-In | 2025-12-01 | 2026-01-10 | 2026-02-22 | -42 | 0.05 | Blocked by A40 - cannot start until piping clears
A42 | Levels 3-4 Electrical Rough-In | 2026-01-11 | 2026-02-20 | 2026-03-05 | -13 | 0 | Sequenced behind A41; some float remains
A50 | Blockwork & Partitions | 2025-11-15 | 2026-01-31 | 2026-01-25 | -8 | 0.55 | Re-sequenced ahead of MEP to recover time
A60 | Internal Finishes | 2026-02-01 | 2026-06-30 | 2026-08-10 | -42 | 0 | Follows electrical rough-in; inherits full delay
A70 | Generator Installation (variation, not yet instructed) | 2026-01-05 | 2026-02-10 | TBC - pending instruction |  | 0 | Generator variation not yet instructed by client
A80 | Commissioning & Handover | 2026-08-11 | 2026-09-04 | 2026-10-16 | -42 | 0 | Forecast handover 16 Oct 2026, 42 days late