## Project Overview
Al Noor Office Building — Project Planning Dataset
Field | Value | Key Deliverable | Acceptance Criterion | Owner
Project ID | ANOB-2026-01 | Site mobilization | Site offices, utilities, fencing and permits operational | Project Manager
Client | Al Noor Properties | Substructure | Foundations and basement accepted by consultant | Civil Manager
Project | Construction of a 5-storey commercial office building | Superstructure | Structural frame completed and surveyed | Structural Engineer
Location | Beirut, Lebanon | Building envelope | Façade watertightness test passed | Architect
Planned Start | 46266 | MEP systems | Testing and commissioning records approved | MEP Manager
Target Completion | 2027-08-31 | Interior finishes | Approved mock-up quality achieved throughout | Finishing Manager
Gross Floor Area | 8,500 m² | Handover | Occupancy permit, as-builts, O&M manuals and training complete | Project Manager
Contract Type | Lump-sum design-bid-build
Original Contract Value | 4850000
Contingency Allowance | 0.08
Working Calendar | 6 days/week, Sunday off

## Activity Schedule
Activity ID | WBS | Activity | Predecessor(s) | Duration (days) | Planned Start | Planned Finish | Responsible | Crew Size | Progress % | Status | Priority | Notes
A001 | 1.1 | Obtain final construction permit |  | 15 | 2026-09-01 | 2026-09-18 | Project Manager | 2 | 100% | Completed | High | Permit expected before physical work
A002 | 1.2 | Mobilize site and temporary facilities | A001 | 10 | 2026-09-19 | 2026-09-30 | Site Manager | 12 | 80% | In Progress | High | Temporary power connection delayed
A003 | 1.3 | Site survey and setting out | A002 | 4 | 2026-10-01 | 2026-10-05 | Surveyor | 4 | 25% | In Progress | High
A004 | 2.1 | Bulk excavation | A003 | 15 | 2026-10-06 | 2026-10-22 | Civil Manager | 18 | 0% | Not Started | High | Rock layer may affect productivity
A005 | 2.2 | Shoring and dewatering | A003 | 20 | 2026-10-06 | 2026-10-29 | Civil Manager | 14 | 0% | Not Started | High | Runs partly in parallel with excavation
A006 | 2.3 | Blinding concrete | A004,A005 | 3 | 2026-10-30 | 2026-11-02 | Civil Manager | 10 | 0% | Not Started | Medium
A007 | 2.4 | Raft reinforcement and formwork | A006 | 18 | 2026-11-03 | 2026-11-23 | Structural Engineer | 28 | 0% | Not Started | High
A008 | 2.5 | Raft concrete pour | A007 | 2 | 2026-11-24 | 2026-11-25 | Structural Engineer | 35 | 0% | Not Started | High | Night pour planned
A009 | 2.6 | Basement walls and columns | A008 | 20 | 2026-11-26 | 2026-12-19 | Structural Engineer | 30 | 0% | Not Started | High
A010 | 3.1 | Ground-floor slab | A009 | 12 | 2026-12-21 | 2027-01-04 | Structural Engineer | 32 | 0% | Not Started | High
A011 | 3.2 | Typical floor 1 structure | A010 | 15 | 2027-01-05 | 2027-01-21 | Structural Engineer | 34 | 0% | Not Started | High
A012 | 3.3 | Typical floor 2 structure | A011 | 15 | 2027-01-22 | 2027-02-08 | Structural Engineer | 34 | 0% | Not Started | High
A013 | 3.4 | Typical floor 3 structure | A012 | 15 | 2027-02-09 | 2027-02-25 | Structural Engineer | 34 | 0% | Not Started | High
A014 | 3.5 | Typical floor 4 structure | A013 | 15 | 2027-02-26 | 2027-03-15 | Structural Engineer | 34 | 0% | Not Started | High
A015 | 3.6 | Roof slab and plant rooms | A014 | 18 | 2027-03-16 | 2027-04-05 | Structural Engineer | 32 | 0% | Not Started | High
A016 | 4.1 | External blockwork | A012 | 35 | 2027-02-09 | 2027-03-22 | Architect | 22 | 0% | Not Started | Medium | Start after two structural floors
A017 | 4.2 | Façade and glazing | A016 | 50 | 2027-03-23 | 2027-05-20 | Façade Manager | 20 | 0% | Not Started | High | Long-lead glazing package
A018 | 5.1 | MEP first fix | A012 | 60 | 2027-02-09 | 2027-04-19 | MEP Manager | 36 | 0% | Not Started | High | Zone-by-zone release
A019 | 5.2 | Internal plaster and screed | A016,A018 | 40 | 2027-04-20 | 2027-06-05 | Finishing Manager | 38 | 0% | Not Started | Medium
A020 | 5.3 | Ceilings and partitions | A019 | 35 | 2027-06-07 | 2027-07-16 | Finishing Manager | 32 | 0% | Not Started | Medium
A021 | 5.4 | Flooring, painting and joinery | A020 | 30 | 2027-07-17 | 2027-08-20 | Finishing Manager | 40 | 0% | Not Started | High | Compressed finish period
A022 | 6.1 | MEP second fix and equipment | A019 | 40 | 2027-06-07 | 2027-07-23 | MEP Manager | 42 | 0% | Not Started | High
A023 | 6.2 | Testing and commissioning | A021,A022 | 15 | 2027-08-21 | 2027-09-07 | Commissioning Manager | 18 | 0% | Not Started | High | Exceeds target date unless recovered
A024 | 7.1 | External works and landscaping | A017 | 25 | 2027-05-21 | 2027-06-18 | Site Manager | 18 | 0% | Not Started | Low
A025 | 7.2 | Final inspection, snagging and handover | A023,A024 | 12 | 2027-09-08 | 2027-09-21 | Project Manager | 20 | 0% | Not Started | High | Current plan is 21 days late

## Resources
Resource ID | Resource / Trade | Type | Available Qty | Unit | Standard Rate / Day | Planned Utilization % | Supplier / Employer | Lead Time (days) | Constraint / Comment
R001 | Project Manager | Staff | 1 | person | 450 | 100% | Main Contractor | 0 | Full-time
R002 | Site Engineers | Staff | 4 | persons | 220 | 90% | Main Contractor | 0 | One engineer assigned to night work during major pours
R003 | Safety Officers | Staff | 2 | persons | 180 | 85% | Main Contractor | 0 | Additional officer required above 120 workers
R004 | Tower Crane | Equipment | 1 | unit | 850 | 95% | Leased | 30 | Critical shared resource
R005 | Mobile Crane 80T | Equipment | 1 | unit | 1250 | 35% | Local Supplier | 7 | Booked only for heavy lifts
R006 | Excavators | Equipment | 2 | units | 600 | 80% | Leased | 5 | Possible rock breaker attachment required
R007 | Dump Trucks | Equipment | 8 | units | 220 | 75% | Haulage Subcontractor | 3 | City traffic restrictions apply
R008 | Concrete Pump | Equipment | 1 | unit | 700 | 45% | Concrete Supplier | 2 | Reserve 72 hours before major pours
R009 | Carpenters | Labor | 24 | workers | 95 | 90% | Main Contractor | 0 | Peak demand during structural cycles
R010 | Steel Fixers | Labor | 22 | workers | 105 | 90% | Subcontractor A | 7 | Shortage risk in peak season
R011 | Masons | Labor | 18 | workers | 85 | 80% | Subcontractor B | 5
R012 | Electricians | Labor | 20 | workers | 110 | 75% | MEP Subcontractor | 10
R013 | Plumbers | Labor | 16 | workers | 105 | 75% | MEP Subcontractor | 10
R014 | HVAC Technicians | Labor | 12 | workers | 125 | 70% | MEP Subcontractor | 21 | Long-lead specialist availability
R015 | Finishing Workers | Labor | 30 | workers | 90 | 80% | Finishes Subcontractor | 14 | May require second shift to recover schedule

## Cost Plan
Cost Code | Package | Original Budget | Committed Cost | Actual Cost to Date | Forecast to Complete | Forecast Final Cost | Variance to Budget | % Spent | Comment
C100 | Preliminaries and site management | 420000 | 310000 | 185000 | 255000 | 440000 | -20000 | 44.05% | Temporary utilities running above allowance
C200 | Excavation, shoring and substructure | 610000 | 525000 | 142000 | 495000 | 637000 | -27000 | 23.28% | Potential rock excavation claim not included
C300 | Structural concrete frame | 1050000 | 910000 | 0 | 1080000 | 1080000 | -30000 | 0% | Steel price escalation exposure
C400 | Façade and external envelope | 730000 | 615000 | 0 | 760000 | 760000 | -30000 | 0% | Glazing quotation valid for 30 days
C500 | Mechanical systems | 640000 | 525000 | 0 | 665000 | 665000 | -25000 | 0% | Chiller procurement pending
C600 | Electrical and low-current systems | 520000 | 435000 | 0 | 535000 | 535000 | -15000 | 0% | Generator specification under review
C700 | Interior finishes and joinery | 560000 | 210000 | 0 | 590000 | 590000 | -30000 | 0% | Final material selections not frozen
C800 | External works and landscaping | 160000 | 55000 | 0 | 175000 | 175000 | -15000 | 0% | Drainage redesign may increase quantities
C900 | Testing, commissioning and handover | 80000 | 10000 | 0 | 90000 | 90000 | -10000 | 0%
C950 | Contingency | 80000 | 0 | 0 | 45000 | 45000 | 35000 | 0% | Remaining management reserve
KPI | Value
Total Original Budget | 4850000
Forecast Final Cost | 5017000
Forecast Variance | -167000
Forecast Overrun % | 3.443%

## Procurement
Package ID | Package | Required On Site | Planned PO Date | Supplier | Quotation Status | Lead Time (days) | Current Status | Risk Rating | Estimated Value | Action Required
P001 | Reinforcement steel | 2026-11-01 | 2026-09-20 | Levant Steel | 3 quotations received | 21 | Technical evaluation | High | 510000 | Lock price and issue PO before quotation expiry
P002 | Ready-mix concrete | 2026-10-30 | 2026-09-25 | Beirut Concrete Co. | Negotiation | 7 | Commercial review | Medium | 430000 | Confirm pumping and night-pour rates
P003 | Aluminium façade and glazing | 2027-03-10 | 2026-10-15 | Cedars Façade Systems | Preferred bidder selected | 120 | Awaiting client approval | Critical | 690000 | Approve shop-drawing schedule and release advance payment
P004 | Chillers and AHUs | 2027-05-01 | 2026-10-01 | Regional HVAC Supplier | Technical clarification | 150 | Delayed | Critical | 310000 | Freeze design and obtain client decision within 10 days
P005 | Main electrical panels | 2027-05-15 | 2026-11-01 | Power Systems SAL | 2 quotations received | 90 | Technical evaluation | High | 175000 | Close short-circuit study
P006 | Diesel generator | 2027-05-20 | 2026-11-15 | GenPro | Specification under review | 105 | On Hold | High | 120000 | Confirm acoustic and emissions requirements
P007 | Elevators | 2027-06-01 | 2026-10-20 | LiftTech | Preferred bidder selected | 180 | Awaiting contract | Critical | 225000 | Issue letter of intent immediately
P008 | Raised flooring | 2027-07-01 | 2027-01-15 | FloorGrid | Budget quotation only | 75 | Not Started | Medium | 95000 | Approve finish and loading criteria
P009 | Doors and architectural joinery | 2027-06-15 | 2027-01-05 | Woodline | Shop drawings pending | 90 | Design development | High | 180000 | Freeze room data sheets

## Risks and Issues
ID | Type | Description | Category | Probability (1-5) | Impact (1-5) | Risk Score | Severity | Owner | Response / Mitigation | Due Date | Status
RI-01 | Risk | Unexpected hard rock during excavation | Technical | 4 | 4 | 16 | High | Civil Manager | Confirm borehole records; allow rock breaker and disposal route | 2026-09-25 | Open
RI-02 | Issue | Temporary electrical connection is 8 days late | Schedule | 5 | 3 | 15 | High | Site Manager | Rent temporary generator and escalate utility application | 2026-09-18 | In Progress
RI-03 | Risk | Reinforcement steel price may rise after quotation validity | Cost | 4 | 4 | 16 | High | Commercial Manager | Negotiate fixed price and early procurement | 2026-09-22 | Open
RI-04 | Risk | Façade shop drawings may not be approved before fabrication slot | Schedule | 4 | 5 | 20 | Critical | Façade Manager | Weekly design workshop and staged approvals | 2026-10-05 | Open
RI-05 | Risk | MEP coordination clashes could delay first fix | Technical | 3 | 5 | 15 | High | BIM Manager | Federated BIM clash review every week | 2026-12-15 | Open
RI-06 | Risk | Shortage of steel fixers during regional peak season | Resource | 3 | 4 | 12 | High | Construction Manager | Framework agreement with backup subcontractor | 2026-10-10 | Open
RI-07 | Risk | Client delays final finish selections | Stakeholder | 4 | 4 | 16 | High | Project Manager | Decision schedule with approval deadlines and mock-ups | 2026-11-30 | Open
RI-08 | Risk | Urban traffic restrictions reduce truck productivity | Logistics | 3 | 3 | 9 | Medium | Logistics Coordinator | Night deliveries and traffic permit | 2026-09-28 | Open
RI-09 | Issue | Current baseline handover is 21 days after target date | Schedule | 5 | 5 | 25 | Critical | Planning Manager | Develop recovery schedule using overlapping and second shifts | 2026-09-20 | In Progress
RI-10 | Risk | Testing and commissioning records may be incomplete | Quality | 2 | 4 | 8 | Medium | Commissioning Manager | Commissioning plan and document tracker from design stage | 2027-01-15 | Open

## Stakeholders
Stakeholder | Organization | Role / Interest | Influence | Interest | Communication Method | Frequency | Owner | Current Concern
Project Sponsor | Al Noor Properties | Funding and strategic decisions | High | High | Steering meeting and dashboard | Monthly | Project Manager | Target completion must not slip
Client Project Manager | Al Noor Properties | Day-to-day client decisions | High | High | Progress meeting | Weekly | Project Manager | Design approvals and cost forecast
Lead Consultant | Design Partners | Design compliance and certification | High | High | Technical coordination meeting | Weekly | Design Manager | Timely RFIs and submittals
Municipality | Beirut Municipality | Permits and inspections | High | Medium | Formal submissions | As required | Project Manager | Compliance with permit conditions
Main Contractor Director | BuildRight SAL | Commercial and delivery performance | High | High | Executive review | Biweekly | Project Manager | Forecast overrun and schedule recovery
Subcontractors | Multiple | Execution of specialist packages | Medium | High | Coordination meeting | Weekly | Construction Manager | Workfront availability and payment
Local Neighbors | Adjacent properties | Noise, traffic and access | Medium | Medium | Notices and hotline | Before disruptive work | Site Manager | Night work and truck movement
Future Tenants | To be confirmed | Operational requirements | Low | Medium | Client-led workshops | Monthly from fit-out stage | Architect | Flexibility and handover readiness

## Change Log
Change ID | Date Raised | Raised By | Description | Reason | Schedule Impact (days) | Cost Impact | Decision Needed By | Status | Decision / Comment
CR-001 | 2026-09-14 | Client | Add a 250 m² executive conference center on Level 4 | New tenant requirement | 18 | 145000 | 2026-09-28 | Under Review | Requires structural and MEP design review
CR-002 | 2026-09-16 | Consultant | Upgrade façade glass specification to higher thermal performance | Energy model compliance | 7 | 85000 | 2026-09-25 | Pending Client Decision | May affect glazing procurement slot
CR-003 | 2026-09-17 | Contractor | Use temporary generator until permanent site power is available | Utility delay | -4 | 18000 | 2026-09-18 | Recommended | Reduces mobilization delay

## Dashboard
Construction Project Planning — Management Dashboard
KPI | Value | Suggested Student Outputs
Contract / Budget | 4850000 | 1. Prepare a corrected baseline and recovery schedule
Forecast Final Cost | 5017000 | 2. Identify the critical path and schedule threats
Forecast Variance | -167000 | 3. Prepare a cost forecast and explain major variances
Schedule Completion | 4.453% | 4. Rank procurement priorities and recommend actions
Open Critical/High Risks | 8 | 5. Update the risk register after reviewing all files
Critical Procurement Items | 3 | 6. Produce a one-page executive report
7. Create a 6-slide client progress presentation