## Slide 1
Al Noor Office Building
Recovery Review & Management Decision Pack
Six-slide client presentation | prepared from supplied project files
Start
1 Sep 2026
Current review
17 Sep 2026
Façade on site
10 Mar 2027
Target handover
31 Aug 2027
Current finish
21 Sep 2027
21-day gap
Al Noor Office Building | Recovery Review

## Slide 2
1) Project situation assessment
Baseline is late, cost is already adverse, and critical procurement/design decisions are on the immediate path.
Schedule gap
21 days
current finish: 21 Sep 2027
Base cost variance
-$167k
3.44% above budget
Remaining contingency
$45k
limited management reserve
Critical procurement
3 items
façade, chillers, elevators
Open high/critical risks
8
risk register requires action
What changed since baseline
• Permit received; mobilization 80% complete, but temporary power is 8 days late.
• Client requested Level 4 executive conference center and façade upgrade review.
• Façade supplier requires an early decision to retain available production slot.
Management implication
The project needs a formal recovery programme now. Without fast decisions, the late baseline can become a wider time-and-cost exposure once change requests and long-lead procurement are added.
Al Noor Office Building | Recovery Review

## Slide 3
2) Revised activity plan: threats to target date
The practical recovery window is concentrated in mobilization, substructure, façade/MEP, finishes and commissioning.
ID
Activity
Threat
Recovery action
A002
Mobilization
Power 8 days late
Approve generator / escalate utility
A004–A005
Excavation + shoring
Hard-rock risk
Pre-check records; standby breaker
A017
Façade + glazing
Slot and approval risk
Immediate client decision + staged approvals
A018/A022
MEP first/second fix
Chiller capacity not frozen
Freeze loads; expedite long-lead package
A021–A025
Finishes to handover
Compressed finish + T&C
Second shift / zonal commissioning
Critical path principle: protect façade/MEP access and convert the final handover period from sequential completion into zonal completion + rolling commissioning.
Al Noor Office Building | Recovery Review

## Slide 4
3) Cost forecast and change exposure
Base forecast is already over budget; unapproved changes could materially increase the gap.
$4.850m
Original budget
$5.017m
Base forecast
$5.265m
All CRs approved
Largest adverse base variances
Concrete frame
-$30k
Façade
-$30k
Finishes
-$30k
Substructure
-$27k
Mechanical
-$25k
Preliminaries
-$20k
Do not treat conference center or façade upgrade as approved. If accepted, they require formal cost/time approval or scope trade-off.
Al Noor Office Building | Recovery Review

## Slide 5
4) Procurement priorities and top risks
Immediate decisions should protect long-lead packages and remove approval blockers.
Procurement priority list
1
Façade + glazing
Critical
2
Chillers / AHUs
Critical
3
Elevators
Critical
4
Reinforcement steel
High
5
Electrical panels
High
6
Diesel generator
High
Top risk themes
1. Late baseline / no recovery approval
2. Façade slot and glazing decision
3. Chiller capacity freeze and procurement
4. Temporary power delay
5. Level 4 conference center change
6. Steel price escalation
Al Noor Office Building | Recovery Review

## Slide 6
5) Recommended management decisions
A controlled recovery should begin now, while unapproved changes remain under formal change control.
APPROVE NOW
• Temporary generator / utility recovery plan with cost approval for USD 18k.
• Recovery programme: resequence, overlap façade/MEP, and start zonal commissioning.
• Procurement task force for façade, chillers, elevators and steel within 10 days.
DECIDE / CONTROL
• Level 4 conference center: defer to post-handover unless time/cost accepted.
• Façade upgrade: accept only with immediate approval and procurement slot protection.
• Chiller capacity and finish selections: freeze by named deadlines.
Recommended position: recover the 21-day gap first. Treat unapproved changes as separate scope decisions with explicit cost, schedule and approval consequences.
Al Noor Office Building | Recovery Review