Al Noor Office Building — Project Recovery Pack

Prepared from supplied project brief, schedule, cost, procurement, risks, meeting notes, and client change request.

# Assumptions

Current baseline completion is 21 September 2027 against the contractual target of 31 August 2027: 21 calendar days late.

No approval is assumed for CR-001 conference center or CR-002 façade upgrade; their schedule/cost effects are shown as potential exposure only.

CR-003 generator is treated as a recommended recovery action, not an approved cost, unless management/client approval is confirmed.

Cost plan forecast final cost of USD 5.017m is the base forecast before unapproved change approvals unless already explicitly included in the cost plan comments.

Working calendar is assumed as 6 days/week, Sunday off as shown in the project overview.

# 1. Concise Project Situation Assessment

| Area | Status | Assessment |
| --- | --- | --- |
| Schedule | Amber/Red | The project is already forecasting handover on 21 Sep 2027, 21 days beyond the 31 Aug 2027 contractual target. Mobilization is 80% complete; temporary power is 8 days late but a generator can recover about 4 days. |
| Cost | Amber/Red | Base forecast final cost is USD 5.017m vs USD 4.850m budget: USD 167k adverse, before unapproved change exposure. Remaining contingency is USD 45k. |
| Procurement | Red | Façade, chillers/AHUs and elevators are critical long-lead packages. Façade production slot and chiller capacity decisions are immediate threats. |
| Design / Change | Red | Client request for Level 4 executive conference center adds potential 18 days and USD 145k; façade upgrade adds potential 7 days and USD 85k. Approvals are not yet confirmed. |
| Risk | Red | Critical risks/issues include late baseline, façade approval slot, temporary power, steel escalation, hard rock, MEP capacity freeze, finish decisions and commissioning readiness. |

# 2. Revised Activity Plan — Activities Threatening Target Completion

| ID | Activity | Current Finish / Window | Threat | Reason |
| --- | --- | --- | --- | --- |
| A002 | Mobilize site and temporary facilities | 18 Sep 2026 | High | Temporary power connection 8 days late; generator can reduce delay by about 4 days. |
| A004/A005 | Bulk excavation / shoring and dewatering | 10–17 Oct 2026 / 10–24 Oct 2026 | High | Possible hard-rock layer at eastern excavation area may reduce productivity and affect start of blinding. |
| A007–A015 | Raft, basement and superstructure frame | 29 Oct 2026–22 Mar 2027 | High | Tower crane, steel fixers and concrete-pour logistics are shared/critical resources; structural path controls envelope and MEP access. |
| A017 | Façade and glazing | 14 Mar–11 May 2027 | Critical | Production slot requires early client decision; glazing upgrade can add 7 days and USD 85k exposure. |
| A018/A022 | MEP first fix / second fix and equipment | 5 Jan–15 Aug 2027 | Critical | Chiller capacity not frozen; chillers/AHUs are 150-day lead-time items. |
| A021 | Flooring, painting and joinery | 9 Jul–12 Aug 2027 | High | Compressed finish period; selections and room data sheets not frozen. |
| A023 | Testing and commissioning | 13–30 Aug 2027 | Critical | Finishes/MEP completion currently push commissioning beyond target unless overlapped or shortened. |
| A025 | Final inspection, snagging and handover | 31 Aug–21 Sep 2027 | Critical | Current handover is 21 days late; recovery must remove entire float deficit. |

# 3. Recovery Strategy Options and Trade-Offs

| Option | Description | Benefits | Trade-offs | Recommendation |
| --- | --- | --- | --- | --- |
| Option 1 — Controlled acceleration | Approve generator, resequence survey/excavation, overlap shoring/excavation, start façade submittals immediately, and overlap commissioning by zones. | Targets 21 days with lowest disruption; uses known USD 18k generator cost. | Limited margin; requires strict daily control and fast design/procurement decisions. | Recommended base recovery. |
| Option 2 — Intensive acceleration | Second shifts for structure/finishes, additional steel-fixer and finishing crews, weekend/night pours, expediting long-lead packages. | Higher probability of recovering 21+ days and absorbing some change impact. | Cost not fully priced in supplied files; higher safety, quality and neighbor-disruption risk. | Use only if Option 1 progress slips after two weeks. |
| Option 3 — Scope/decision protection | Defer Level 4 conference center to post-handover tenant fit-out; approve/reject façade upgrade by decision deadline; freeze chiller capacity and finish selections. | Protects contractual completion and avoids unapproved USD 230k change exposure. | Client may lose desired enhancement before opening; may require formal change control. | Recommended for unapproved changes unless client accepts time/cost impact. |
| Option 4 — Commercially managed change | Accept conference center and façade upgrade with formal extension of time and added cost; reserve procurement slots immediately. | Preserves upgraded scope and reduces procurement uncertainty. | Likely worsens completion beyond target unless combined with costly acceleration. | Only if client prioritizes enhanced scope over date/cost. |

# 4. Cost Forecast and Largest Adverse Variances

| Forecast item | Value | Comment |
| --- | --- | --- |
| Base original budget | USD 4.850m | Approved contract value from cost plan. |
| Base forecast final cost | USD 5.017m | Current forecast before unapproved change approvals unless already captured. |
| Base adverse variance | USD 167k over budget | 3.44% overrun; remaining contingency only USD 45k. |
| If CR-003 generator approved | +USD 18k | Forecast becomes USD 5.035m; may reduce mobilization delay by about 4 days. |
| If CR-001 + CR-002 approved | +USD 230k | Forecast becomes USD 5.247m before generator; schedule exposure +25 days. |
| If all listed CRs approved | +USD 248k | Forecast becomes USD 5.265m, approx. USD 415k over original budget. |

| Package | Adverse variance | Explanation / response |
| --- | --- | --- |
| Structural concrete frame | -USD 30k | Steel price escalation exposure; lock reinforcement steel quotation. |
| Façade and external envelope | -USD 30k | Glazing quotation valid for 30 days; production slot depends on approval. |
| Interior finishes and joinery | -USD 30k | Final material selections not frozen; compressed finish period. |
| Excavation, shoring and substructure | -USD 27k | Possible hard-rock claim not included. |
| Mechanical systems | -USD 25k | Chiller procurement pending and capacity not frozen. |
| Preliminaries and site management | -USD 20k | Temporary utilities running above allowance; generator would add USD 18k if approved. |

# 5. Procurement Priority List

| Rank | Package | Priority | Why it matters | Immediate action |
| --- | --- | --- | --- | --- |
| 1 | Aluminium façade and glazing | Critical | Required on site 10 Mar 2027; 120-day lead time; awaiting client approval. | Approve specification/shop-drawing schedule and release advance payment. |
| 2 | Chillers and AHUs | Critical | Required 1 May 2027; 150-day lead time; delayed and design not frozen. | Freeze capacity within 10 days; close technical clarifications. |
| 3 | Elevators | Critical | Required 1 Jun 2027; 180-day lead time; awaiting contract. | Issue letter of intent immediately. |
| 4 | Reinforcement steel | High | Price may rise after quotation validity; needed early in substructure. | Lock price and issue PO before expiry. |
| 5 | Main electrical panels | High | 90-day lead; short-circuit study outstanding. | Close study and complete technical evaluation. |
| 6 | Diesel generator | High | 105-day lead; spec on hold; temporary generator also needed now. | Confirm acoustic/emissions requirements; decide temporary vs permanent scope. |
| 7 | Doors and architectural joinery | High | 90-day lead; shop drawings pending. | Freeze room data sheets. |
| 8 | Ready-mix concrete | Medium | Pumping/night-pour rates not closed. | Confirm rates before raft/major pours. |
| 9 | Raised flooring | Medium | Budget quotation only. | Approve finish/loading criteria. |

# 6. Updated Top-10 Risk and Issue Register

| Rank | Type | Risk / Issue | Severity | Owner | Mitigation / next action |
| --- | --- | --- | --- | --- | --- |
| 1 | Issue | Current baseline handover is 21 days late | Critical | Planning Manager | Approve recovery programme; weekly executive look-ahead. |
| 2 | Risk | Façade production slot missed / glazing upgrade decision late | Critical | Façade Manager | Client decision by deadline; staged approvals and LOI. |
| 3 | Risk | Chiller capacity not frozen / HVAC long lead | Critical | MEP Manager | Freeze loads and chiller capacity; procurement task force. |
| 4 | Issue | Temporary power connection 8 days late | High | Site Manager | Approve generator or utility escalation plan. |
| 5 | Risk | Level 4 conference center change adds 18 days and USD 145k | High | Project Manager | Formal change control; defer to post-handover unless time/cost accepted. |
| 6 | Risk | Reinforcement steel price escalation | High | Commercial Manager | Lock quotation and issue PO. |
| 7 | Risk | Unexpected hard rock in excavation | High | Civil Manager | Confirm records; standby rock breaker and disposal route. |
| 8 | Risk | MEP coordination clashes delay first fix | High | BIM Manager | Weekly federated clash review and zone release. |
| 9 | Risk | Finish selections / room data sheets delayed | High | Architect / PM | Decision schedule and mock-ups. |
| 10 | Risk | Commissioning/as-built records incomplete | Medium | Commissioning Manager | Start commissioning tracker now; package-by-package evidence. |

7. One-Page Management Report

| Topic | Management message |
| --- | --- |
| Overall status | RED: Current programme misses target by 21 days; cost forecast is USD 167k over budget before unapproved changes. |
| Required decisions | Approve generator strategy; freeze chiller capacity; decide façade glazing upgrade; decide whether Level 4 conference center is in base handover or later tenant fit-out. |
| Recommended plan | Adopt controlled acceleration immediately: generator + resequencing + façade/MEP task force + zonal commissioning. Protect completion by deferring unapproved Level 4 change unless client accepts time/cost impact. |
| Cost position | Base forecast USD 5.017m vs USD 4.850m budget. If all listed CRs are approved, forecast exposure rises to about USD 5.265m, USD 415k above original budget. |
| Procurement focus | Façade/glazing, chillers/AHUs, elevators and reinforcement steel are the first four priorities. |
| Next 14 days | Issue recovery programme; place/lock critical procurement; complete design decision log; run weekly risk/decision meeting; report recovered days and cost drawdown. |

Note: Figures and dates are based only on supplied project files. Unapproved changes are shown as exposure, not approved scope.